## Status
AMAT project status and decisions
Status as of | 2026-09-27
Overall status | Gray
Open actions | 3
Open risks | 3
Open issues | 1
Deliverables QA Pass | 1
Decision / gate | Evidence required | Owner | Needed by | Status | Next action
G0 Kickoff alignment | Charter, RACI, ways of working, first data request | TBD WITH CLIENT |  | Not Started | Validate sponsor, decision rights and scope
G1 Data readiness | Data tracker, dictionary, quality review and approved assumptions | TBD WITH CLIENT |  | Not Started | Assign data owners and transfer route
G2 Shared market understanding | Workshop decisions, questions and actions | TBD WITH CLIENT |  | Not Started | Confirm audience and learning objectives
G3 Baseline accepted | Gap model, quality flags and management summary | TBD WITH CLIENT |  | Not Started | Confirm reporting boundary and target definition
ID | Top risk / issue | Impact | Response / containment | Owner | Next check | RAG
R-001 | Decision rights may remain unclear after kickoff | Approval delay and rework | Validate sponsor, decision body and gate owners in 1.1 | Project Lead |  | Amber
R-002 | Site and consumption data may not support intended analysis grain | Gap and scenario precision may be limited | Profile completeness early and agree assumption policy | Data Lead |  | Amber
R-003 | Market disclosure authority is not yet defined | Outreach may expose client information or reduce response quality | Obtain written disclosure boundary before 2.2 | Project Lead |  | Amber

## Minutes
Meeting minutes register
Meeting ID | Date | Title | Participants / roles | Objective | Conclusion | Decision IDs | Action IDs | Note owner | Status
MTG-DEMO-001 | 2026-10-01 | SYNTHETIC kickoff preparation example | Project Lead; Sustainability owner | Confirm success definition and first data request | Demo only. Replace after client meeting. | D-DEMO-001 | ACT-DEMO-001 | PMO | Not Started

## Actions
Action log
Action ID | Action | Workstream | Owner | Due date | Status | Dependency | Evidence | Notes
ACT-PRE-001 | Confirm client sponsor, decision body and day-to-day owner | 1.1 | Project Lead |  | Not Started | Kickoff scheduling |  | TBD WITH CLIENT
ACT-PRE-002 | Confirm approved file transfer and AI / SaaS rules | 1.1 / Shared | Project Lead |  | Not Started | Client security contact |  | TBD WITH CLIENT
ACT-PRE-003 | Approve information disclosure boundary before supplier outreach | 2.2 | Project Lead |  | Not Started | AMAT Procurement / Legal |  | TBD WITH CLIENT

## Risks
Risk log
Risk ID | Cause | Risk event | Impact | Likelihood | Impact level | Rating | Response | Owner | Status
R-001 | Decision roles are not confirmed | Approvals stall or feedback conflicts | Delay and rework | Medium | High | High | Validate RACI and gate owners in 1.1 | Project Lead | Open
R-002 | Client data grain and quality are unknown | Baseline cannot support requested analysis | Reduced precision or scope change | Medium | High | High | Use 1.2 quality review and agreed assumption policy | Data Lead | Open
R-003 | Disclosure authority is not documented | Market outreach shares too much or too little | Confidentiality or market response risk | Medium | High | High | Approve disclosure ladder before 2.2 | Project Lead | Open

## Issues
Issue log
Issue ID | Fact pattern | Impact | Containment | Resolution plan | Owner | Target date | Status
I-DEMO-001 | SYNTHETIC / DEMO DATA: required consumption file arrives without meter IDs | Cannot reconcile site baseline | Pause model refresh and preserve raw file | Request mapping table and validate duplicates | Data Lead |  | Deferred

## Decisions
Decision log
Decision ID | Date | Decision | Decision maker | Options considered | Rationale | Conditions | Affected artifacts | Status
D-ARCH-001 | 2026-09-27 | Use a document-first, gate-based delivery architecture for repository v0.1 | Optimum pre-delivery build | Deck-heavy; document-first; minimal placeholders | Supports concise client decisions and reusable internal method | Client-specific expectations remain TBD WITH CLIENT | Master Blueprint; Architecture | Complete

## Assumptions
Assumption log
Assumption ID | Statement | Basis | Affected output | Impact if wrong | Validation method | Owner | Review date | Status
A-001 | Core stakeholders may include Taiwan sustainability, Procurement, Facilities, Finance, Legal and regional / global owners | HYPOTHESIS based on typical enterprise procurement governance | 1.1; 1.3; 1.6 | Wrong audience or approval path | Validate stakeholder map at kickoff | Project Lead |  | Open
A-002 | Annual residual gap is the first planning basis; finer granularity depends on data availability | HYPOTHESIS for pre-delivery model design | 1.4; 1.5 | Model may require redesign | Review data grain in 1.2 | Data Lead |  | Open

## Changes
Scope and change log
Change ID | Date raised | Request | Requester | Scope / time / quality impact | Recommendation | Decision | Decision date | Status
CHG-DEMO-001 | 2026-10-10 | SYNTHETIC / DEMO DATA: add hourly matching analysis | Client stakeholder | Requires interval data and added model scope | Assess data availability before acceptance | No decision. Demo only. |  | Deferred

## Sources
Source log
Source ID | Type | Title / description | Publisher / owner | Publication date | Location / URL | Access date | Reliability | Scope / limitations | Used in | Status
SRC-001 | Internal brief | User-provided AMAT pre-delivery repository brief | Project requester | 2026-09-27 | Project request | 2026-09-27 | Primary task definition | Does not confirm AMAT-specific facts | Repository architecture and acceptance criteria | Active

## Stakeholders
Stakeholder map
Stakeholder ID | Role hypothesis | Function | Influence | Interest | Decision role | Information need | Engagement plan | Status label | Validation status
STK-001 | Taiwan sustainability / RE100 owner | Sustainability | High | High | Baseline / roadmap owner | Gap, options, reporting implications | Kickoff interview and workshop | HYPOTHESIS | TBD WITH CLIENT
STK-002 | Procurement | Procurement | High | High | Market process and commercial approval | Supplier universe, process, terms | Kickoff interview; 2.x governance | HYPOTHESIS | TBD WITH CLIENT
STK-003 | Facilities / site energy owners | Operations | Medium | High | Data and implementation owner | Meters, load, wheeling and operational needs | Data interview and workshop | HYPOTHESIS | TBD WITH CLIENT
STK-004 | Finance | Finance | High | Medium | Budget / risk / approval | Cost, settlement, credit and accounting | Scenario and decision reviews | HYPOTHESIS | TBD WITH CLIENT
STK-005 | Legal | Legal | High | Medium | Legal advice and contract approval | NDA, risk allocation, contracting | Boundary review; 3.x | HYPOTHESIS | TBD WITH CLIENT
STK-006 | Regional / global sustainability and procurement | Regional / Global | High | Medium | Policy and final alignment | RE100 policy, global approvals, portfolio fit | Targeted interviews and gates | HYPOTHESIS | TBD WITH CLIENT

## Client Questions
Client question log
Question ID | Question | Why needed | Answer owner | Needed by | Status | Answer / evidence | Affected workstreams
Q-001 | Who is the sponsor, day-to-day owner and decision body for each gate? | RACI, cadence and approvals | TBD WITH CLIENT | Kickoff | Open |  | 1.1; all
Q-002 | What sites, meters, periods and data grain define the analysis boundary? | Baseline and model design | Facilities / data owner | Before G1 | Open |  | 1.2; 1.4; 1.5
Q-003 | How does AMAT define eligible renewable procurement and target years for this project? | Residual gap and option eligibility | Sustainability / RE100 owner | Before G3 | Open |  | 1.4; 1.5; 2.x
Q-004 | What client identity and volume information may Optimum disclose at each market stage? | Confidentiality and response quality | Sponsor / Procurement / Legal | Before 2.2 | Open |  | 2.1; 2.2; 2.5
Q-005 | Which legal counsel provides formal legal advice and who owns contract redlines? | Commercial / legal interface | AMAT Legal | Before 3.2 | Open |  | 3.2–3.5

## Deliverables
Deliverable register
Deliverable ID | Workstream | Artifact / package | Audience | Owner | Reviewer | Due date | Version | Status | Acceptance basis | Location
DEL-ARCH | Architecture | Acceptance criteria, architecture and master blueprint | Founder / Project Lead | Repository author | Project Lead |  | v0.1 | QA Pass | Architecture QA | Root / shared
DEL-SHARED | Shared | Project controls, confidentiality and market conduct | Project team | Repository author | Project Lead |  | v0.1 | In Progress | Shared QA | shared
DEL-TRAIN | Training | New hire guide and task brief | New hires / reviewers | Repository author | Project Lead |  | v0.1 | In Progress | Training usability QA | training
DEL-01 | 1.1 | 1.1 Kickoff | TBD WITH CLIENT | TBD WITH OPTIMUM | Project Lead |  | v0.1 | Not Started | Workstream Definition of Done | workstreams/01
DEL-02 | 1.2 | 1.2 Data requirements | TBD WITH CLIENT | TBD WITH OPTIMUM | Project Lead |  | v0.1 | Not Started | Workstream Definition of Done | workstreams/02
DEL-03 | 1.3 | 1.3 Taiwan market workshop | TBD WITH CLIENT | TBD WITH OPTIMUM | Project Lead |  | v0.1 | Not Started | Workstream Definition of Done | workstreams/03
DEL-04 | 1.4 | 1.4 RE100 gap analysis | TBD WITH CLIENT | TBD WITH OPTIMUM | Project Lead |  | v0.1 | Not Started | Workstream Definition of Done | workstreams/04
DEL-05 | 1.5 | 1.5 Portfolio scenario analysis | TBD WITH CLIENT | TBD WITH OPTIMUM | Project Lead |  | v0.1 | Not Started | Workstream Definition of Done | workstreams/05
DEL-06 | 1.6 | 1.6 Alignment roadmap | TBD WITH CLIENT | TBD WITH OPTIMUM | Project Lead |  | v0.1 | Not Started | Workstream Definition of Done | workstreams/06
DEL-07 | 2.1 | 2.1 Market scan | TBD WITH CLIENT | TBD WITH OPTIMUM | Project Lead |  | v0.1 | Not Started | Workstream Definition of Done | workstreams/07
DEL-08 | 2.2 | 2.2 Market engagement | TBD WITH CLIENT | TBD WITH OPTIMUM | Project Lead |  | v0.1 | Not Started | Workstream Definition of Done | workstreams/08
DEL-09 | 2.3 | 2.3 Short-term procurement | TBD WITH CLIENT | TBD WITH OPTIMUM | Project Lead |  | v0.1 | Not Started | Workstream Definition of Done | workstreams/09
DEL-10 | 2.4 | 2.4 Long-term procurement | TBD WITH CLIENT | TBD WITH OPTIMUM | Project Lead |  | v0.1 | Not Started | Workstream Definition of Done | workstreams/10
DEL-11 | 2.5 | 2.5 Targeted RFQ | TBD WITH CLIENT | TBD WITH OPTIMUM | Project Lead |  | v0.1 | Not Started | Workstream Definition of Done | workstreams/11
DEL-12 | 2.6 | 2.6 Evaluation and DD | TBD WITH CLIENT | TBD WITH OPTIMUM | Project Lead |  | v0.1 | Not Started | Workstream Definition of Done | workstreams/12
DEL-13 | 3.1 | 3.1 Commercial alignment | TBD WITH CLIENT | TBD WITH OPTIMUM | Project Lead |  | v0.1 | Not Started | Workstream Definition of Done | workstreams/13
DEL-14 | 3.2 | 3.2 Contract review | TBD WITH CLIENT | TBD WITH OPTIMUM | Project Lead |  | v0.1 | Not Started | Workstream Definition of Done | workstreams/14
DEL-15 | 3.3 | 3.3 Negotiation round 1 | TBD WITH CLIENT | TBD WITH OPTIMUM | Project Lead |  | v0.1 | Not Started | Workstream Definition of Done | workstreams/15
DEL-16 | 3.4 | 3.4 Negotiation decision | TBD WITH CLIENT | TBD WITH OPTIMUM | Project Lead |  | v0.1 | Not Started | Workstream Definition of Done | workstreams/16
DEL-17 | 3.5 | 3.5 Signing readiness | TBD WITH CLIENT | TBD WITH OPTIMUM | Project Lead |  | v0.1 | Not Started | Workstream Definition of Done | workstreams/17
DEL-18 | 3.6 | 3.6 Execution tracking | TBD WITH CLIENT | TBD WITH OPTIMUM | Project Lead |  | v0.1 | Not Started | Workstream Definition of Done | workstreams/18

## Schedule
Master schedule and decision gates
Milestone ID | Workstream | Milestone | Owner | Start | Finish | Predecessor | Gate | Exit evidence | Status
M-G0 | 1.1 | G0 Kickoff alignment | Project Lead |  |  |  | G0 | Charter and governance accepted | Not Started
M-G1 | 1.2 | G1 Data readiness | Data Lead |  |  | M-G0 | G1 | Data quality and assumption policy accepted | Not Started
M-G2 | 1.3 | G2 Shared market understanding | Project Lead |  |  | M-G0 | G2 | Workshop learnings and actions accepted | Not Started
M-G3 | 1.4 | G3 Baseline accepted | Client RE100 owner |  |  | M-G1; M-G2 | G3 | Residual gap and quality flags accepted | Not Started
M-G4 | 1.5 | G4 Portfolio direction | Steering group |  |  | M-G3 | G4 | Portfolio direction selected | Not Started
M-G5 | 1.6 | G5 Market engagement authority | Sponsor / Procurement / Legal |  |  | M-G4 | G5 | Roadmap and disclosure boundary approved | Not Started
M-G6 | 2.5 | G6 RFQ launch | Procurement |  |  | M-G5 | G6 | Bidder list, package and evaluation rules approved | Not Started
M-G7 | 2.6 | G7 Shortlist | Decision body |  |  | M-G6 | G7 | Shortlist and open DD approved | Not Started
M-G8 | 3.1 | G8 Negotiation mandate | Authorized decision makers |  |  | M-G7 | G8 | Objectives and authority approved | Not Started
M-G9 | 3.4 | G9 Preferred terms | Approval body |  |  | M-G8 | G9 | Residual risks and terms accepted | Not Started
M-G10 | 3.5 | G10 Signing readiness | Contract owner |  |  | M-G9 | G10 | Signing and implementation readiness confirmed | Not Started
M-G11 | 3.6 | G11 BAU transition | Operations owner |  |  | M-G10 | G11 | Governance and BAU handover accepted | Not Started