# AMAT Taiwan Renewable Electricity Advisory — Project Charter and Ways of Working v0.1

> Status：PRE-KICKOFF DRAFT。除 KNOWN 外皆須在正式專案驗證。本文件不是已同意的 AMAT scope 或 governance。

## 1. Charter at a glance

| Item | v0.1 position | Status / validation |
| --- | --- | --- |
| Project purpose | 建立可執行的台灣再生能源採購路徑：從需求 / gap、portfolio、market engagement、RFQ、評估、談判到 execution governance | HYPOTHESIS；與 SOW / sponsor 確認 |
| Primary outcome | 讓 AMAT 能以 evidence-based、cross-functional、可審批的方式選擇並落地採購組合 | HYPOTHESIS |
| Success evidence | 決策口徑一致、inputs 可追溯、選項可比較、風險被清楚接受、合約與 execution handoff 完整 | HYPOTHESIS |
| Client sponsor | TBD WITH CLIENT | kickoff 前指定 |
| Delivery owner | Optimum Project Lead / Taiwan Lead | 確認 named owner |
| Phase structure | 1.x define / align；2.x market / evaluate；3.x negotiate / execute | KNOWN methodology；commercial scope 待核對 |
| Working method | Define → MVP → Review → Correct → Expand | KNOWN Optimum delivery principle |

## 2. Objectives and non-objectives

### Objectives

先確認 client decisions 與使用者，再決定分析深度與格式。

建立 baseline / residual gap 與採購組合的可追溯口徑。

用一致資訊欄位掃描、接觸、比較與篩選市場選項。

把 commercial review、legal advice、negotiation authority 與 internal approval 清楚區分。

將簽約成果交接成可長期追蹤的 execution governance。

### Non-objectives unless explicitly contracted

提供法律、稅務、會計、工程或投資保證。

代表 AMAT 作未授權承諾、簽約、揭露 client identity / exact volume。

為特定供應商背書，或保證市場價格 / availability / project COD。

以未驗證 AMAT-specific facts 建立 recommendation。

## 3. Initial scope map and decision gates

| Gate | Decision | Evidence required | Default approver hypothesis |
| --- | --- | --- | --- |
| G0 Kickoff | charter、scope interpretation、owners、cadence | expectation answers、RACI、workplan | Client sponsor + Optimum lead |
| G1 Requirements | baseline boundary、target、data treatment | data quality report、interview findings | Sustainability + Facilities + Procurement |
| G2 Portfolio | target portfolio / scenarios to pursue | gap model、scenario comparison、risk / cost / timing | Steering group |
| G3 Market launch | disclosure boundary、supplier universe、engagement method | market scan、conflict check、authorization | Sponsor + Procurement + Legal |
| G4 RFQ | bidder list、requirements、evaluation weights | bidder pack、response template、scorecard | Procurement / decision owner |
| G5 Shortlist | shortlist / reserve / stop | normalized bids、DD、risk assessment | Steering group |
| G6 Negotiation mandate | priorities、walk-away、concession authority | commercial term baseline、issue list | Authorized decision group |
| G7 Select / sign | counterparty / structure、risk acceptance、signing authority | final comparison、legal advice、readiness checklist | Client-authorized approvers |
| G8 Go-live | readiness / transition to BAU | CP closure、systems / wheeling / certificates / contacts | Business owner + implementation owners |
| G9 Performance | corrective action / renewal / escalation | expected-vs-actual、certificate / settlement reconciliation | BAU governance |

All AMAT-specific approvers are TBD WITH CLIENT.

## 4. Stakeholder and RACI hypothesis

| Activity | Client sponsor | Sustainability / RE100 | Procurement | Facilities / Energy | Finance | Legal | Global / Regional | Optimum |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Success criteria / scope | A | R/C | C | C | C | C | C | R |
| Baseline / load data | I | C | I | R | C | I | C | A/C |
| Target / claims treatment | I | R | C | C | I | C | A/C | C |
| Portfolio recommendation | A | R | R | C | C | C | C | R |
| Market engagement | I | C | A/R | C | I | C | I | R |
| Evaluation / shortlist | A | C | R | C | C | C | C | R |
| Contract / negotiation | A | C | R | C | C | A/R | C | commercial R / legal C only |
| Signing / implementation | A | C | R | R | C | R | C | C / PMO |

RACI is a HYPOTHESIS. Named people、authority limits與 legal counsel role 必須在 G0 / G1 確認。

## 5. Ways of working

### Before any material task

Task brief 必須回答 Objective、Expected Output、Intended Use、Approach、Inputs、Unknowns、Questions to Confirm、First MVP、Review Point、Definition of Done。沒有這十項，不進入長時間 production。

### Review rhythm

| Forum | Default purpose | Proposed cadence | Output |
| --- | --- | --- | --- |
| Analyst / Optimum review | 方法、evidence、preliminary judgement | working days as needed | corrected MVP / review note |
| Client working session | 解開資料 / 假設 / design 問題 | biweekly HYPOTHESIS | decisions / actions / client questions |
| Steering / sponsor review | gate decision、risk acceptance、scope change | monthly or at gate HYPOTHESIS | signed-off decision record |
| Market interaction | 取得可比較的供應資訊，不做未授權承諾 | controlled by 2.2 protocol | interaction record / red flags |

### Review SLA hypothesis

Pre-read：重要 decision material 原則上會前 2 個工作天。

Working review：指定 reviewer 原則上 2 個工作天內回覆或說明新日期。

Decision：若未定案，必須記錄 pending owner、missing evidence、latest-needed date，不把沉默視為同意。

Urgent issues：confidentiality、false commitment、material scope / price / legal exposure 立即升級。

## 6. Decision process

1.  Analyst 明確陳述 decision requested，而不只報告活動。

2.  將 KNOWN、HYPOTHESIS、TBD、SYNTHETIC、RESEARCH REQUIRED 分開。

3.  列 feasible options、recommendation、trade-offs、required evidence、reversibility。

4.  Decision owner 可選 Approve / Approve with conditions / Request revision / Defer / Stop。

5.  48 小時內將 rationale、conditions、actions、owner、date、affected artifacts 寫入 Decision log。

6.  對 scope、cost、timeline 或 assumption baseline 的重大改變，進 Change log。

## 7. Issue and escalation process

| Trigger | Immediate action | Escalation owner | Target response |
| --- | --- | --- | --- |
| Confidentiality / accidental disclosure | Stop / Report / Contain / Document | Project Lead + authorized security contact | Immediate |
| Unclear authority / market commitment | Pause external response | Project Lead + Procurement / Legal | Before reply |
| Data issue changes decision materially | Flag range / sensitivity; do not hide | Workstream owner + sponsor | Before gate |
| Scope / timeline impact | Log change with options and consequences | Project Lead + client sponsor | Next steering or urgent review |
| Potential conflict | Pause affected contact; document; consider recusal / barrier | Project Lead | Before engagement |

## 8. First four-week workplan hypothesis

| Timing | Client-facing objective | Optimum MVP | Decision / handoff |
| --- | --- | --- | --- |
| Week 0 | kickoff / governance | charter、questions、initial RACI、controls | G0 |
| Week 1 | launch data / interviews | data request guide、tracker、interview guide | data owners / dates |
| Week 2 | understand Taiwan procurement choices | workshop pre-read / workshop | workshop learning / decisions |
| Week 3 | lock baseline method | synthetic model + initial client mapping | calculation boundary / gaps |
| Week 4 | preview portfolio choices | 2–3 scenario MVP | inputs for G2 |

Actual dates、sequencing與 availability 均 TBD WITH CLIENT。

## 9. Initial expectation-validation questions

| Question | Why it matters | Proposed owner | Needed by |
| --- | --- | --- | --- |
| 成功完成後，AMAT 內部要做出哪 3–5 個 decisions？ | 決定 deliverable 的用途與深度 | Client sponsor | G0 |
| 哪些成果需 Taiwan、regional、global approval？ | 決定 stakeholder / timeline / pre-read | Sponsor | G0 |
| 本案優先解決 target compliance、cost visibility、execution certainty 或其他目的？ | 決定 scenario weights | Sponsor + Sustainability | G1 |
| Sites / entities / load / target boundary 如何定義？ | 決定 1.4 model scope | Sustainability + Facilities | G1 |
| 誰擁有 demand forecast、existing procurement、budget 與 contract data？ | 決定 data request owner | Sponsor | Week 1 |
| 何時可揭露 AMAT identity、volume band、site 或 timing 給市場？ | 避免資訊過度揭露 | Procurement + Legal | Before 2.2 |
| 哪些 commercial / legal topics 必須由 AMAT counsel 主導？ | 區分 commercial review / legal advice | Legal | Before 3.2 |
| 哪些 timeline 是 externally fixed，哪些可調？ | 形成 critical path | Sponsor | G0 |
| 既有 internal procurement / approval / vendor onboarding 規則是什麼？ | RFQ、shortlist、signing 可執行性 | Procurement | G1 / G4 |
| 決策延遲或資料缺口時，誰可接受 assumption / range？ | 防止 analysis 無限等待 | Sponsor | G0 |

## 10. Immediate post-kickoff actions

48 小時內發出 minutes、decision / assumption / action log 更新。

指派 1.2 data owners 與 1.3 participant / workshop objectives。

確認文件 repository、classification、review naming / version rule。

對 proposal / SOW 與 charter 差異提出 change / clarification，不默認擴張 scope。

安排 G1 requirements review 與 G2 portfolio review 的 provisional dates。