# AMAT Master Delivery Blueprint v0.1

## Purpose and reading guide

本文件把 1.1–3.6 的 purpose、client question、audience、activities、inputs、deliverables、dependencies、hypotheses、open questions 與下一階段 handoff 放在同一份管理視圖。它是 pre-contract v0.1，不代表 AMAT 已核准 scope、組織、資料、時程或 procurement position。

## Delivery logic

1.x 先建立 mandate、資料與共同語言，再把需求缺口轉成 portfolio 與 roadmap。2.x 以 roadmap 為邊界測試市場、取得可比較提案並形成 shortlist。3.x 鎖定商業條件、審閱風險分配、談判、簽署並轉入執行治理。Shared PM、confidentiality、market conduct 與 training 橫跨全程。

## 1.1 專案啟動與工作方式確認

Purpose：確認成功定義、scope、roles、ways of working、decision rights、review rhythm 與 first 30-day plan。

Client question：我們要一起回答哪些問題，誰在何時做什麼決定，成果要如何被 AMAT 使用？

Audience：HYPOTHESIS - sponsor、Taiwan sustainability / RE100 owner、Procurement、Facilities、Finance、Legal、regional / global stakeholders。

Activities：expectation validation interviews、scope boundary review、RACI、meeting cadence、decision / change process、deliverable acceptance、initial risk workshop。

Inputs：proposal / SOW（若有）、known correspondence、stakeholder hypothesis、target dates、data access constraints。

Deliverables：Kickoff Deck、Project Charter、Ways of Working、RACI、Workplan、cadence、decision process、ARID structure、expectation validation questions。

Dependencies：正式 SOW / contracting status、client sponsor availability、Optimum staffing。

Key hypotheses：AMAT 需要跨 Taiwan / regional / global alignment；現階段真正使用情境與 approval path 未明。

Open questions：什麼叫成功、in / out of scope、final users、approval rights、preferred communication、document security、escalation SLA？

Connection to next stage：核准的 governance 與 first data request 啟動 1.2；stakeholder list 與 learning needs 啟動 1.3。

## 1.2 資料與需求蒐集

Purpose：建立可追蹤、可解釋、足以支撐 1.4–1.6 的資料與需求基礎。

Client question：哪些資料與 stakeholder evidence 足以建立 baseline、理解限制並設計 procurement options？

Audience：Taiwan sustainability、Facilities / site energy owners、Procurement、Finance、Legal、data owners。

Activities：分批 data request、data dictionary、quality profiling、stakeholder interviews、gap triage、assumption approval、source logging。

Inputs：site / meter list、monthly or interval consumption、tariff / bill data、existing renewable contracts / certificates、target definition、load changes、budget / accounting preferences、internal policies。

Deliverables：Data Request Guide、Data Request Tracker.xlsx、Data Dictionary.xlsx、quality checklist、interview guide、requirements question list、data gap process。

Dependencies：1.1 governance、access and confidentiality rules、client owner assignments。

Key hypotheses：不同 sites / functions 可能由不同 data owners 管理；資料 grain 與一致性可能不足以直接做 hourly matching。

Open questions：coverage period、unit、meter hierarchy、forecast ownership、existing procurement treatment、data retention / transfer requirements？

Connection to next stage：clean input schema、quality flags 與 approved assumptions餵入 1.4；non-numeric requirements餵入 1.5 / 1.6。

## 1.3 台灣市場與再生能源採購工作坊

Purpose：建立 AMAT stakeholders 的共同市場語言，讓後續 portfolio 與 roadmap 決策有足夠理解與明確問題。

Client question：台灣採購機制如何影響 AMAT 的 volume、tenor、price、flexibility、risk、certificate 與 execution choices？

Audience：HYPOTHESIS - Taiwan sustainability / RE100 owner、Procurement、Facilities、Finance、Legal、regional / global sustainability / procurement、relevant decision makers。

Activities：pre-read / pulse check、market mechanics teaching、electricity / contract / certificate flow、option comparison、constraint discussion、decision exercise、question capture。

Inputs：validated stakeholder / learning needs、current public market research、1.2 early findings、AMAT questions。

Deliverables：Workshop Design Document、Workshop Deck、Facilitator Guide、participant design、discussion questions、expected decisions / learnings、follow-up actions。

Dependencies：1.1 sponsor alignment；client-facing facts需完成 source validation。

Key hypotheses：stakeholders 對 wheeling、retailer、T-REC、PPA risk 與 internal decision implications 的理解程度不一致。

Open questions：需要教育、alignment 還是 decision session？哪些敏感議題不適合全體討論？需要中英文哪一種？

Connection to next stage：workshop 的 agreed principles、questions、risk preferences 與 owner gaps 餵入 1.4–1.6。

## 1.4 需求與 RE100 缺口分析

Purpose：以可追溯資料計算 baseline、target、existing eligible procurement 與 residual gap，並揭示 data quality / sensitivity。

Client question：在各 target year，AMAT 要補足多少符合其定義的再生能源需求，哪些數字仍不確定？

Audience：Sustainability / RE100 owner、Facilities、Finance、Procurement、Project Lead。

Activities：boundary definition、data mapping、unit normalization、baseline / forecast、eligibility mapping、gap calculation、sensitivity、management interpretation。

Inputs：1.2 clean data、target rules、growth / efficiency assumptions、existing procurement and certificate data。

Deliverables：Methodology Document、Gap Analysis Model.xlsx、synthetic demo dataset、management summary、decision output。

Dependencies：1.2 data completeness、1.3 shared terminology、client confirmation of reporting boundary。

Key hypotheses：年度 gap 是第一版 planning basis；若 data 支援再擴充 site / month / load shape granularity。

Open questions：reporting boundary、market-based / location-based treatment、contracted volume recognition、forecast horizon、uncertainty tolerance？

Connection to next stage：year-by-year residual gap、quality flag 與 sensitivity range直接成為 1.5 demand input。

## 1.5 採購組合與情境分析

Purpose：把 residual gap 轉成可比較的 procurement portfolios，顯示 cost、timing、tenor、technology、flexibility 與 concentration risk。

Client question：哪些組合能在可接受的成本與風險下滿足短、中、長期目標？

Audience：Sustainability、Procurement、Finance、Facilities、Legal、decision makers。

Activities：option screening、scenario definition、volume allocation、cost logic、timing / tenor mapping、risk scoring、dependency and sensitivity analysis。

Inputs：1.4 gap、1.2 requirements、1.3 preferences、RESEARCH REQUIRED market assumptions。

Deliverables：Portfolio Methodology、Scenario Model.xlsx、assumptions、option comparison、management / decision output。

Dependencies：gap basis accepted；市場假設的來源與日期可追溯。

Key hypotheses：初版至少需 Base、Flexibility-priority、Long-term coverage-priority 三種 synthetic scenarios；名稱與參數於客戶 review 後調整。

Open questions：cost definition、budget guardrail、acceptable tenor、technology / supplier concentration、flexibility value、risk tolerance？

Connection to next stage：selected or hybrid scenario 的 volumes、waves、risks 與 dependencies進入 1.6 roadmap。

## 1.6 跨部門對齊與 RE100 路徑圖

Purpose：將 portfolio direction 轉成有 owners、decision gates、timeline、approval points 與 2.x briefs 的行動路徑。

Client question：AMAT 應先做什麼、何時決定、誰負責，如何由短期 coverage 過渡到中長期主力採購？

Audience：cross-functional steering group、regional / global approvers、workstream owners。

Activities：scenario alignment、dependency mapping、approval design、procurement waves、risk ownership、resource / calendar review。

Inputs：1.4 gap、1.5 scenarios、1.3 stakeholder outputs、1.1 governance。

Deliverables：Alignment / Roadmap Document、Roadmap Deck、decision gates、owner / dependency matrix、short / medium / long-term roadmap、2.x transition briefs。

Dependencies：preliminary scenario direction；decision owners and calendars。

Key hypotheses：roadmap 需容許 near-term bridging 與 long-term contracting 並行，不預先假定特定供應商或結構。

Open questions：which gates need global approval、procurement calendar、market engagement disclosure、resourcing、interim coverage policy？

Connection to next stage：approved market questions、volume bands、timing、option scope 與 disclosure boundary定義 2.1–2.6。

## 2.1 市場掃描與供應商盤點

Purpose：建立可追溯的 market universe、supplier / developer / retailer / project categorization 與 preliminary screening。

Client question：哪些市場參與者與供應機會值得進一步接觸，基於什麼證據？

Audience：Optimum market / commercial team、AMAT Procurement / Sustainability；外部不直接分享 raw judgement。

Activities：research protocol、source collection、entity / project ID、category and field mapping、evidence confidence、initial screen。

Inputs：1.6 market brief、public sources、Optimum legitimate market knowledge、disclosure constraints。

Deliverables：Market Scan Methodology、Market Landscape.xlsx、screening logic、source log、preliminary summary、research protocol。

Dependencies：scope boundary、source hygiene、market conduct rules。

Key hypotheses：public information 不足以確認 live availability / commercial terms，需 2.2 驗證。

Open questions：geographic / technology / maturity scope、excluded parties、conflict check、client identity disclosure？

Connection to next stage：screened longlist、unknown fields 與 contact priority餵入 2.2、2.3、2.4。

## 2.2 初步市場接觸與供應條件確認

Purpose：在受控資訊邊界內驗證供應意願、availability、structure 與 key conditions，不造成 false commitment。

Client question：市場是否能供應我們考慮的 volume / timing / structure，條件範圍與 red flags 是什麼？

Audience：Optimum engagement lead、AMAT authorized Procurement / Sustainability；selected suppliers。

Activities：conflict / disclosure check、neutral outreach、questionnaire、meeting、comparable capture、fact confirmation、market feedback synthesis。

Inputs：2.1 longlist、1.6 requirement bands、approved information boundary、contact protocol。

Deliverables：Market Engagement Protocol、questionnaire、email / meeting scripts、Interaction Tracker.xlsx、market feedback memo、red flag checklist。

Dependencies：client authorization to engage and disclose；confidentiality process。

Key hypotheses：匿名或低資訊 outreach 可先測試基本 fit；具體報價需 2.5 controlled process。

Open questions：which facts can be disclosed、can Optimum name AMAT、recording rules、supplier NDA need、response status？

Connection to next stage：availability、structure、timing、price basis 與 red flags更新 2.3 / 2.4 assessment及 2.5 design。

## 2.3 短期補充型採購方案評估

Purpose：評估能補足近期 gap 或 timing mismatch 的較短期、較具彈性方案。

Client question：哪些方案可在目標時間內提供合格 coverage，代價與 delivery risk 為何？

Audience：Sustainability、Procurement、Finance、Legal / reporting stakeholders。

Activities：option eligibility、availability、price structure、term、certificate treatment、flexibility、delivery and counterparty risk comparison。

Inputs：1.4 near-term gap、1.5 scenario needs、2.1 / 2.2 market evidence、client policy。

Deliverables：Short-term Procurement Assessment Memo、comparison workbook、decision brief。

Dependencies：confirmed RE100 / internal eligibility、market data freshness。

Key hypotheses：短期方案主要是 bridge / residual tool，不預設長期策略由其取代。

Open questions：acceptable instrument / geography / vintage、minimum term、renewal risk、accounting / budget treatment？

Connection to next stage：recommended short-term requirements與 evaluation criteria進入 2.5 RFQ 或直接 decision gate（若客戶核准）。

## 2.4 中長期主力型採購方案評估

Purpose：評估能提供中長期 volume coverage 的主要 procurement structures 與 project risks。

Client question：哪些結構與供應專案能支持長期目標，price certainty、credit、generation、wheeling 與 contract complexity 如何取捨？

Audience：Sustainability、Procurement、Finance / Treasury、Facilities、Legal、decision makers。

Activities：structure mapping、project maturity / COD、supply profile、volume / tenor / price、credit、curtailment / generation、wheeling、T-REC、contract complexity comparison。

Inputs：1.5 / 1.6 long-term needs、2.1 / 2.2 evidence、client credit / risk parameters。

Deliverables：Long-term Procurement Assessment Memo、commercial comparison model、decision brief。

Dependencies：project / supplier information quality、internal tenure and credit appetite。

Key hypotheses：不同結構無法只用 headline price 比較，需 normalize risk allocation、profile、COD 與 certificate / wheeling interfaces。

Open questions：preferred structure、tenor ceiling、volume flexibility、credit support、curtailment allocation、COD tolerance？

Connection to next stage：long-term commercial requirements、project DD fields 與 risk questions進入 2.5 / 2.6。

## 2.5 定向提案／報價徵詢

Purpose：以一致 instructions、assumptions、pricing template 與 Q&A process 取得可比較、可評估的供應提案。

Client question：如何讓 selected bidders 回覆同一需求、揭露必要風險並避免後續比較失真？

Audience：selected bidders、AMAT Procurement / Legal / Sustainability、Optimum process team。

Activities：requirement freeze、bidder instruction、response schema、pricing / assumptions、briefing、Q&A、deadline / amendment control、submission compliance。

Inputs：1.6 procurement brief、2.3 / 2.4 criteria、2.1 / 2.2 bidder evidence、approved disclosure and legal terms。

Deliverables：RFQ / RFP Package.docx、Supplier Response Template.xlsx、Q&A process、bidder briefing material、commercial assumptions、response rules。

Dependencies：G6 approval、bidder list、confidentiality / NDA route、evaluation methodology frozen before launch。

Key hypotheses：targeted process 比 open market call 更符合 preselected fit；實際 approach 為 TBD WITH CLIENT。

Open questions：procurement policy、mandatory terms、bid validity、alternative bids、clarification protocol、deadline and timezone？

Connection to next stage：標準化 response fields、proposal IDs 與 exceptions直接輸入 2.6 scorecard / DD。

## 2.6 方案評估、盡職調查與候選名單

Purpose：將提案的 commercial value、technical / execution feasibility、counterparty / project risk 與 unresolved DD 整合為 shortlist recommendation。

Client question：哪些方案值得進入 final alignment / negotiation，原因、風險與未決事項是什麼？

Audience：Procurement、Sustainability、Finance、Facilities、Legal、approval body。

Activities：compliance screen、normalization、weighted / gated evaluation、DD、risk assessment、scenario impact、reference / evidence check、shortlist workshop。

Inputs：2.5 responses、2.3 / 2.4 assessment、2.1 / 2.2 evidence、approved criteria。

Deliverables：Evaluation Methodology、Scorecard.xlsx、Due Diligence Checklist、risk assessment、commercial comparison、Decision Memo、shortlist output。

Dependencies：evaluation rules locked before seeing final scores；clarification process documented。

Key hypotheses：score 支持而不取代 judgement；critical gate failure 可高於 weighted score。

Open questions：weight / gate approval、conflict reviewers、risk acceptance authority、number of shortlisted options？

Connection to next stage：shortlisted offers、normalized terms、risks、open DD 與 recommendation進入 3.1。

## 3.1 最終需求與商業條件對齊

Purpose：在談判前鎖定 final volume / timing / structure assumptions、objectives、priorities、trade-offs 與 internal mandate。

Client question：我們要談成什麼，哪些條件可交換，哪些需升級或不可接受？

Audience：authorized decision makers、Procurement、Sustainability、Finance、Facilities、Legal、negotiation team。

Activities：shortlist refresh、demand / scenario update、term baseline、priority / fallback / walk-away discussion、approval of mandate。

Inputs：2.6 shortlist、1.4 / 1.5 updates、latest proposals、client policies and approvals。

Deliverables：Commercial Alignment Memo、Commercial Term Tracker.xlsx、issue list、negotiation objectives、alignment meeting material。

Dependencies：decision authority and legal interface confirmed。

Key hypotheses：volume / timing 可能因 market evidence 更新；變更需透過 decision log / scope control。

Open questions：authority limits、fallback supplier / structure、approval thresholds、communications route？

Connection to next stage：approved term IDs、priority、target、fallback and escalation rule餵入 3.2–3.4。

## 3.2 合約與交易條件審閱

Purpose：從 commercial / execution 視角辨識條款、risk allocation 與 operability，並與法律顧問分工。

Client question：draft contract 在 settlement、delivery、wheeling、certificates、default、termination、change、force majeure、credit、guarantee、CP 等方面如何影響交易？

Audience：Procurement、commercial owners、Finance、Facilities / operations、AMAT Legal / external counsel。

Activities：clause mapping、commercial impact、legal question routing、issue prioritization、operability test、owner assignment。

Inputs：3.1 mandate、contract drafts、proposal and clarification record、client policies、legal advice。

Deliverables：Contract Review Playbook、Commercial / Legal Issue Tracker.xlsx、clause checklist、risk allocation checklist。

Dependencies：正式法律意見由 AMAT counsel 提供；Optimum 不作法律結論。

Key hypotheses：許多條款同時有 commercial 與 legal 面向，需要單一 issue ID 共同管理。

Open questions：review protocol、privilege / document handling、redline owner、turnaround SLA、which counsel has final legal call？

Connection to next stage：prioritized issue list、client position、commercial impact 與 legal owner成為 3.3 agenda。

## 3.3 第一輪談判與修正

Purpose：依 mandate 處理最高優先議題，記錄 counterpart position、concessions、impact 與 follow-up。

Client question：第一輪應先解決哪些議題，哪些 concession 可以交換，何時升級？

Audience：negotiation team、authorized client leads、supplier counterpart、Legal where needed。

Activities：pre-brief、agenda / role assignment、negotiation、real-time issue capture、post-meeting record、draft update and impact review。

Inputs：3.1 objectives、3.2 issue list / draft、2.6 commercial evidence、authority matrix。

Deliverables：Negotiation Strategy Memo、Negotiation Tracker.xlsx、meeting brief template、post-meeting record。

Dependencies：approved spokesperson、communication channel、legal attendance / review rule。

Key hypotheses：先處理高價值 / 高依賴議題能避免在低影響條款過早消耗 concession。

Open questions：supplier decision authority、meeting sequence、redline exchange protocol、what can be agreed in room？

Connection to next stage：updated positions、concessions、commercial impact、unresolved issues與 decision asks進入 3.4。

## 3.4 後續談判與內部決策

Purpose：收斂 remaining issues，呈現 final scenarios、incremental commercial impact 與需要 AMAT 接受的 residual risk。

Client question：在現有 terms 下應接受、再談、切換方案或停止？

Audience：approval body、sponsor、Procurement、Sustainability、Finance、Legal、operations owners。

Activities：position refresh、scenario comparison、risk acceptance、approval questions、conditional decision、final negotiation rounds。

Inputs：3.3 tracker、revised drafts / offers、3.1 objectives、3.2 risk positions。

Deliverables：Decision Memo、position tracker、final scenario comparison、risk acceptance record、decision pack。

Dependencies：decision rights and financial / legal impact available。

Key hypotheses：所有 remaining issues 應標為 accept / negotiate / escalate / walk-away / post-signing action，不留無 owner 的 open item。

Open questions：approval forum、quorum、documentation standard、conditional approval validity？

Connection to next stage：approved terms、residual risks、conditions與 owners直接進入 3.5 readiness。

## 3.5 簽約與執行準備

Purpose：在簽約前確認條款、authority、conditions precedent、data / system、wheeling、certificate、supplier contact 與 transition 均可執行。

Client question：我們是否真的準備好簽署並從 day one 履約，尚缺哪些 evidence 或 owner action？

Audience：authorized signatories、Procurement、Legal、Finance、Facilities / operations、Sustainability、supplier implementation team。

Activities：document completeness、signature authority、CP mapping、responsibility matrix、system / data / contact setup、dry-run、handover readiness review。

Inputs：final draft、3.4 approvals、supplier implementation plan、internal system and process requirements。

Deliverables：Signing Readiness Checklist、Conditions Precedent Tracker.xlsx、responsibility matrix、execution readiness、transition plan。

Dependencies：final legal approval、authorized signatures、clear owner for each CP and implementation milestone。

Key hypotheses：signing date 與 delivery start 之間可能存在 CP / setup critical path，需與 contract timeline 對齊。

Open questions：signature mechanics、CP evidence standard、system owner、wheeling / certificate lead time、go-live escalation？

Connection to next stage：milestone IDs、CP status、owner、supplier contacts、baseline obligations與 evidence repository交給 3.6。

## 3.6 採購方案落地與執行追蹤

Purpose：建立 recurring governance，追蹤 milestones、expected vs actual delivery、certificates、reconciliation、commercial issues 與 BAU transition。

Client question：如何確保合約按預期交付、問題被及時處理、證書與財務紀錄可對帳並可持續運作？

Audience：contract / operations owner、Sustainability、Finance / AP、Facilities、Procurement、Legal as needed、supplier operations。

Activities：milestone / delivery tracking、exception management、certificate ledger、reconciliation、commercial issue log、periodic review、lessons learned、BAU handover。

Inputs：3.5 handover、contract obligations、meter / settlement / certificate data、supplier reports、client reporting needs。

Deliverables：Execution Governance Document、Implementation Tracker.xlsx、recurring review format、periodic client reporting template、BAU transition pack。

Dependencies：data flows、system owners、supplier SLA、issue escalation and retention rules。

Key hypotheses：初期需較高頻 governance，穩定後轉為 BAU cadence；實際頻率為 TBD WITH CLIENT。

Open questions：source of truth、tolerance / dispute threshold、certificate retirement ownership、reporting calendar、audit evidence retention？

Connection to next stage：正式移交 BAU；重大 change 透過 shared change control 重新進入 appropriate workstream。

## Cross-cutting controls

Shared PM：status、minutes、actions、risks、issues、decisions、assumptions、changes、sources、stakeholders、questions、deliverables、schedule、version / review。

Training：task definition、MVP、preliminary judgement、review readiness、1.x → 2.x capability progression。

Confidentiality：classification、need-to-know、file / device / cloud / AI / SaaS handling、anonymization、incident response。

Market conduct：information minimisation、neutral outreach、no false commitment、no gossip、no cross-supplier disclosure、conflict awareness、evidence-based communication。

## Kickoff calibration priorities

第一週優先確認：success / intended use、stakeholders / decision rights、scope boundary、data and confidentiality rules、target / RE100 interpretation、timeline / approvals、market disclosure authority、legal counsel interface、reporting cadence。所有未確認事項保留 TBD WITH CLIENT，不透過文字完整度掩蓋未知。